Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories,

Story Points)

| Date | 13 February 2026 |
| --- | --- |
| Team ID | LTVIP2026TMIDS65779 |
| Project Name | Online Payments Fraud Detection using Machine Learning |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation

| Sprint | Functional Requirement (Epic) | User Story No. | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Data Collection & Exploration | USN-1 | As a data analyst, I can import and inspect transaction datasets to understand fraud distribution and data quality. | 3 | High | Data Team |
| Sprint-1 | Data Preprocessing | USN-2 | As a developer, I can clean data, handle missing values, and encode features for fraud modeling. | 4 | High | ML Team |
| Sprint-1 | EDA Visualization | USN-3 | As a team member, I can visualize fraud trends using charts and correlation analysis. | 2 | Medium | Data Team |
| Sprint-2 | Feature Engineering | USN-4 | As a developer, I can create | 3 | High | ML Team |

|  |  |  | behaviorbased features (transaction frequency, deviation, time patterns). |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-2 | Model Development | USN-5 | As a user, I can get fraud prediction using a trained ML model. | 5 | High | ML Team |
| Sprint-2 | Model Evaluation | USN-6 | As a reviewer, I can view accuracy, precision, recall, F1score, and ROC-AUC metrics. | 3 | High | ML Team |
| Sprint-3 | Backend API | USN-7 | As a developer, I can create API endpoints to process transaction inputs and return predictions. | 4 | High | Backend Team |
| Sprint-3 | Model Serving | USN-8 | As a developer, I can load saved model and preprocessing artifacts for real-time inference. | 3 | High | Backend Team |
| Sprint-4 | Monitoring Dashboard | USN-9 | As a fraud analyst, I can view flagged transactions and fraud statistics in a dashboard. | 3 | Medium | Frontend Team |

Project Tracker, Velocity & Burndown Chart

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 9 | 7 Days | 15 Feb 2026 | 21 Feb 2026 | 9 | 21 Feb 2026 |
| Sprint-2 | 11 | 7 Days | 22 Feb 2026 | 28 Feb 2026 | 11 | 28 Feb 2026 |
| Sprint-3 | 7 | 7 Days | 01 Mar 2026 | 07 Mar 2026 | 7 | 07 Mar 2026 |
| Sprint-4 | 5 | 5 Days | 08 Mar 2026 | 12 Mar 2026 | 5 | 12 Mar 2026 |

# Velocity

If sprint duration is 7 days and the team completes approximately 9–11 story points per sprint, average velocity ≈ 1.3–1.5 story points/day. This helps forecast completion timelines for additional fraud detection enhancements.

# Burndown Chart (Description)

A burndown chart tracks remaining story points versus time across each sprint. It helps visualize development progress, monitor delays, and ensure timely deployment of the fraud detection system. The chart can be generated using Agile tracking tools like Jira or Azure DevOps.

# References

Atlassian Agile Project Management – Sprints, Epics, Story Points, Velocity, and Burndown Charts documentation.